## Gantt Chart Table
WBS ID | Task Name | Duration (Days) | Start Week | End Week | Dependencies | Responsible
1 | Initiation Phase | 3 | Week 1 | Week 1 | – | Huzaifa
1.1 | Define project objectives | 1 | Week 1 | Week 1 | – | Huzaifa
1.2 | Identify stakeholders and prepare charter | 1 | Week 1 | Week 1 | 1.1 | Huzaifa
1.3 | Conduct project kick-off meeting | 1 | Week 1 | Week 1 | 1.2 | Both
2 | Planning Phase | 5 | Week 1 | Week 2 | 1 | Huzaifa
2.1 | Develop project scope and WBS | 2 | Week 1 | Week 2 | 1.3 | Huzaifa
2.2 | Create risk and issue management plans | 2 | Week 1 | Week 2 | 2.1 | Both
2.3 | Prepare Gantt chart and project schedule | 1 | Week 2 | Week 2 | 2.2 | Huzaifa
3 | Design Phase | 4 | Week 2 | Week 3 | 2 | Nameer
3.1 | Design chatbot architecture and flow | 2 | Week 2 | Week 2 | 2.3 | Nameer
3.2 | Define API structure and database | 1 | Week 2 | Week 3 | 3.1 | Nameer
3.3 | Design chatbot UI mockups | 1 | Week 3 | Week 3 | 3.2 | Nameer
4 | Development Phase | 6 | Week 3 | Week 4 | 3 | Nameer
4.1 | Build chatbot backend (NLP + intents) | 3 | Week 3 | Week 4 | 3.3 | Nameer
4.2 | Integrate with knowledge base (Zendesk / SharePoint) | 2 | Week 3 | Week 4 | 4.1 | Nameer
4.3 | Implement escalation feature | 1 | Week 4 | Week 4 | 4.2 | Nameer
5 | Testing Phase | 4 | Week 4 | Week 5 | 4 | Both
5.1 | Conduct functional testing | 2 | Week 4 | Week 4 | 4.3 | Both
5.2 | Perform UAT and collect feedback | 1 | Week 5 | Week 5 | 5.1 | Both
5.3 | Fix bugs and retest chatbot | 1 | Week 5 | Week 5 | 5.2 | Nameer
6 | Deployment Phase | 3 | Week 5 | Week 5 | 5 | Both
6.1 | Deploy chatbot on web & WhatsApp | 1 | Week 5 | Week 5 | 5.3 | Nameer
6.2 | Prepare analytics dashboard | 1 | Week 5 | Week 5 | 6.1 | Huzaifa
6.3 | Conduct user training session | 1 | Week 5 | Week 5 | 6.2 | Huzaifa
7 | Closure Phase | 2 | Week 5 | Week 5 | 6 | Both
7.1 | Compile final documentation & lessons learned | 1 | Week 5 | Week 5 | 6.3 | Nameer
7.2 | Conduct project evaluation against MOV | 1 | Week 5 | Week 5 | 7.1 | Both
7.3 | Prepare final presentation | 1 | Week 5 | Week 5 | 7.2 | Both

## Gantt Chart
Phase | Week 1 | Week 2 | Week 3 | Week 4 | Week 5
Initiation | ███
Planning | █████ | █
Design |  | ████ | █
Development |  |  | ██████ | █
Testing |  |  |  | ████ | █
Deployment |  |  |  |  | ███
Closure |  |  |  |  | ██

## Risk Register
Risk ID | Phase | Risk Description | Probability | Impact | Response Strategy | Owner
R1 | 4.0 – Development | Integration issues between chatbot and Zendesk/SharePoint APIs may cause system delays. | Medium | High | Mitigate – Use test sandbox API keys and perform incremental integration tests. | Nameer
R2 | 5.0 – Testing | Chatbot accuracy below 70 % target during UAT. | High | High | Mitigate – Add more training data and fallback responses; re-train model. | Nameer
R3 | 2.0 – Planning / 7.0 – Closure | Version control conflicts or lost updates on GitHub. | Medium | Medium | Prevent – Use branching workflow and peer review before merging. | Both
R4 | 3.0 – Design / 4.0 – Development | Delays due to time constraints from course load. | High | Medium | Mitigate – Follow weekly milestones and use Jira board for task visibility. | Huzaifa
R5 | 6.0 – Deployment | Data privacy breach from using real customer data in testing. | Low | High | Prevent – Use anonymized datasets and secure storage. | Huzaifa
R6 | 5.0 – Testing / 6.0 – Deployment | Environment failure during demo (poor internet or server crash). | Medium | High | Contingency – Keep offline demo backup and recorded demo video. | Both

## Issue Management Strategy
Issue ID | Phase | Description | Priority | Responsible | Status | Resolution / Follow-up
I1 | 4.2 – Integrate with Knowledge Base | Chatbot not retrieving answers from SharePoint due to API permission error. | High | Nameer | Resolved | Updated OAuth token scope and tested new API connection.
I2 | 5.1 – Functional Testing | Chatbot looping responses when question contains punctuation. | High | Nameer | Resolved | Added text cleaning function and re-tested inputs.
I3 | 5.2 – User Acceptance Testing | Users report slow responses at peak queries. | Medium | Both | Open | Optimize API call queue and limit session timeouts.
I4 | 2.3 – Prepare Schedule | Excel Gantt chart formatting inconsistent with Word report. | Low | Huzaifa | Resolved | Re-exported chart as image and embedded correctly.
I5 | 6.1 – Deployment | WhatsApp channel token expired before demo. | Medium | Huzaifa | Resolved | Generated new token and updated environment variables.

## Change Request Logs
Change ID | Phase | Change Description | Reason / Trigger | Impact (Time / Cost / Scope / Quality) | Decision / Status | Approval Authority | Action Taken
C01 | 3.0 – Design | Add a chatbot analytics dashboard to monitor performance metrics. | Stakeholder requested visibility of response accuracy. | Time: +2 days Scope: +1 deliverable | Approved | Project Sponsor | Added analytics module in 6.2 phase.
C02 | 4.0 – Development | Integrate chatbot with both Zendesk and SharePoint instead of one. | Enhanced client requirement. | Time: +3 days Cost: +10% dev effort Scope: Expanded integration | Approved | Project Sponsor | Adjusted WBS 4.2 & updated Gantt chart.
C03 | 5.0 – Testing | Include stress testing for 100+ simultaneous users. | Identified risk of performance lag. | Time: +1 day Quality: Improved reliability | Approved | Project Manager | Added new test case in 5.1 Functional Testing.
C04 | 6.0 – Deployment | Switch demo environment from Azure Web App to local Flask host due to limited internet. | Internet instability during dry runs. | Time: 0 Scope: Minor platform change | Approved | Project Sponsor | Updated environment configuration and documentation.
C05 | 7.0 – Closure | Extend final submission by 2 days to include updated screenshots. | Schedule overlap with other unit deliverables. | Time: +2 days Quality: Improved final report | Approved | Unit Facilitator | Updated project timeline and notified assessor.